## Sheet1
Sprint Backlog
Sun 4th Jan 2015 - Sun 18th Jan 2015 | [17 empty] | To Do
SPRINT UNSUCESSFUL - very ill during the first week and then was on holiday 13th - 17th | [17 empty] | In Progress
1) The user shall be able to create an account | Duration time in hours | Status | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Done
Create PHP Querys for implementation in sprint (i.e. only tables needed for sprint) - changed to asp.net during sprint | 4 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) The user shall be able to create an account | Duration time in hours | Status | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun
Sync code | 3 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) The user shall be able to add a recipe | Duration time in hours | Status | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun
Create GUI | 25 | In Progress | 15 | 15 | 15 | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8
Sync code | 15 | To Do | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
SQLite database tables | 6 | To Do | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Database code | 20 | To Do | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Additional Tasks | Duration time in hours | Status | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 73 |  | 61 | 61 | 61 | 61 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58