## Sheet1
Sprint Backlog
Mon 2nd Feb 2015 - Mon 16th Feb 2015 | [17 empty] | To Do
In Progress
Done
3) The user shall be able to edit a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Edit Recipe View | 15 | In Progress | 15 | 3 | 3 | 3 | 3 | 3 | 3
Sync code | 25 | In Progress | 25 | 25 | 25 | 25 | 15 | 8 | 2
SQLite database tables | 6 | Done | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0
Database code | 20 | Done | 20 | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional Tasks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 66 |  | 66 | 54 | 54 | 38 | 18 | 11 | 5 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0