## Sheet1
Sprint Backlog
Mon 19th Jan 2015 - Mon 2nd Feb 2015 | [17 empty] | To Do
In Progress
Done
1) The user shall be able to add a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Create GUI | 8 | In Progress | 8 | 4 | 4 | 4 | 4
Sync code | 15 | In Progress | 15 | 15 | 15 | 10 | 6
SQLite database tables | 6 | In Progress | 6 | 3 | 4 | 4 | 3
Database code | 20 | In Progress | 20 | 20 | 10 | 8 | 8
2) The user shall be able to delete a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Database code | 12
Sync code | 12
Additional Tasks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 73 |  | 49 | 42 | 33 | 26 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0