## Sheet1
Sprint Backlog
Mon 19th Jan 2015 - Mon 2nd Feb 2015 | [17 empty] | To Do
SPRINT UNSUCESSFUL - very ill during the first week and then was on holiday 13th - 17th | [17 empty] | In Progress
Done
1) The user shall be able to add a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Create GUI | 8 | In Progress | 8 | 4
Sync code | 15 | To Do | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
SQLite database tables | 6 | In Progress | 6 | 3
Database code | 20 | To Do | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
2) The user shall be able to delete a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Database code | 12
Sync code | 12
Additional Tasks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 73 |  | 49 | 42 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35