## Sheet1
Sprint Backlog
Mon 16th Feb 2015 - Mon 2nd Mar 2015 | [17 empty] | To Do
In Progress
Done
The user shall be able to add and view contributers (Server went down on Sun 15th and Mon 16th limited progress) | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Sync code | 20 | Done | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The user shall be able to delete contributers (Server went down on Sun 15th and Mon 16th limited progress) | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Delete view | 10 | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database code | 10 | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sync code | 20 | Done | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The user shall be able to edit a cookbook (Server went down on Sun 15th and Mon 16th limited progress) | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
View | 7 | Done | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database Code | 5 | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sync code | 20 | Done | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GUI Design Changes | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Cookbook And Recipe Pages | 60 | Done | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 30 | 0 | 0 | 0 | 0 | 0
Action Bar | 100 | Done | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 50 | 10 | 0 | 0
Images | 120 | To Do | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
| Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Additional Tasks | Ongoing | To Do
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | 372 |  | 372 | 340 | 340 | 340 | 320 | 280 | 280 | 280 | 280 | 250 | 220 | 170 | 130 | 120 | 120
Total Time