## Sheet1
Sprint Backlog
Mon 2nd Mar 2015 - Mon 16h Mar 2015 | [17 empty] | To Do
In Progress
Done
GUI Design Changes | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Images | 120 | In Progress | 120 | 110 | 100 | 60 | 30 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0
The ability to delete recipes and cookbooks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Database design | 10 | To Do | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Application code | 40 | To Do | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Database code | 30 | To Do | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Sync code | 60 | To Do | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Additional Tasks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 260 |  | 260 | 250 | 240 | 200 | 170 | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0