## Sheet1
Sprint Backlog
Mon 19th Jan 2015 - Mon 2nd Feb 2015 | [17 empty] | To Do
In Progress
Done
1) The user shall be able to add a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Create GUI | 8 | Done | 8 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sync code | 15 | Done | 15 | 15 | 15 | 10 | 6 | 14 | 12 | 12 | 12 | 10 | 3 | 3 | 4 | 0 | 0
SQLite database tables | 6 | Done | 6 | 3 | 4 | 4 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0
Database code | 20 | Done | 20 | 20 | 10 | 8 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) The user shall be able to view a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Recipe list view | 14 | Done | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database code | 10 | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recipe view page | 14 | Done | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) The user shall be able to edit a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Edit recipe view | 25 | In Progress | / | / | / | / | / | / | / | / | / | / | / | / | / | 25 | 15
Additional Tasks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 112 |  | 87 | 80 | 71 | 64 | 59 | 67 | 57 | 40 | 12 | 13 | 6 | 3 | 4 | 25 | 15