## Sheet1
Sprint Backlog
Mon 16th Mar 2015 - Mon 30th Mar 2015 | [17 empty] | To Do
In Progress
Done
The ability to do a basic search | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Add additional recipe features to aid search | 40 | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recipe search | 40 | Done | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cookbook search | 20 | Done | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User search | 20 | Done | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The ability for the user to add reviews | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Database code | 8 | Done | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Application code | 15 | Done | 15 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sync | 10 | Done | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The ability for the user to clone a recipe | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Application code | 10 | Done | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Misc | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Password Security | 8 | Done | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recipe image share | 5 | Done | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Search suggestions | 5 | Done | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional clone | 6 | Done | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delete querys in server | 5 | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 0 | 0 | 0 | 0
The ability to explore recipes | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
GUI interface | 15 | Done | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0
Database code | 10 | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
Adding the ability to add and delete prep and ingred in the edit page | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
GUI code | 25 | Done | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5 | 0 | 0 | 0
Database code | 10 | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0
Sync code | 10 | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 12 | 0
Additional Tasks | Duration time in hours | Status | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 262 |  | 202 | 142 | 129 | 99 | 86 | 81 | 81 | 81 | 80 | 60 | 52 | 25 | 20 | 12 | 0