## Sheet1
Sprint Backlog
Sat 20th Dec 2014 - Sat 3rd Jan 2015 | [17 empty] | To Do
In Progress
1) Create Databases | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Done
Create SQL Server database based on database diagram | 4 | In Progress | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create PHP Querys for implementation in sprint | 8 | To Do | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create SQLite database for implementation in sprint | 8 | To Do | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) Ability to add a user | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Add account | 10 | To Do | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sign user in | 10 | To Do | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delete account | 10 | To Do | 10
Sign in/sign up pages | 7 | To Do | 7
3) Ability for user to add, edit and delete recipes | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Add recipe | 10 | To Do | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Edit recipe | 10 | To Do | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delete recipe | 10 | To Do | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
View recipe | 14 | To Do | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional Tasks | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 101 |  | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0