## Sheet1
Sprint Backlog
Sat 20th Dec 2014 - Sat 3rd Jan 2015 | [17 empty] | To Do
In Progress
1) Create Databases | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Done
Create SQL Server database based on database diagram | 4 | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create PHP Querys for implementation in sprint (i.e. only tables needed for sprint) - changed to asp.net during sprint | 8 | In Progress | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 20 | 20 | 15 | 15 | 15 | 8 | 4
Create SQLite database for implementation in sprint (i.e. only tables needed for sprint) | 8 | Done | 9 | 9 | 9 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) The user shall be able to create an account | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Basic add account | 10 | Done | 10 | 10 | 10 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sync code | 15 | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 20 | 20 | 20 | 12 | 6 | 3
GUI page sign up/sign in and move add account code to GUI | 17 | Done | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sign user in | 10 | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 20 | 10 | 0 | 0 | 0
Additional Tasks | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Exception and error catching | Ongoing | In Progress
Refactoring | Ongoing | In Progress
Unit Tests | Ongoing | In Progress
Total Time | 72 |  | 70 | 69 | 69 | 69 | 56 | 50 | 50 | 41 | 45 | 50 | 55 | 45 | 27 | 14 | 7