## Sheet1
Sprint Backlog
Sat 20th Dec 2014 - Sat 3rd Jan 2015 | [17 empty] | To Do
In Progress
1) Create Databases | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Done
Create SQL Server database based on database diagram | 4 | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create PHP Querys for implementation in sprint (i.e. only tables needed for sprint) | 8 | In Progress | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create SQLite database for implementation in sprint (i.e. only tables needed for sprint) | 8 | Done | 9 | 9 | 9 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) Ability to add a user | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Basic add account | 10 | Done | 10 | 10 | 10 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sync code | 15 | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
GUI page sign up/sign in and move add account code to GUI | 17 | Done | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sign user in | 10 | To Do | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Delete account code | 7 | To Do | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
3) Ability for user to add, edit and delete recipes | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Basic add recipe code | 10 | To Do | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add recipe code GUI | 10 | To Do | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additional Tasks | Duration time in hours | Status | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat
Exception and error catching | Ongoing | To Do
Refactoring | Ongoing | To Do
Unit Tests | Ongoing | To Do
Total Time | 99 |  | 97 | 96 | 96 | 96 | 83 | 77 | 77 | 68