## Sheet1
Recipes For Life - Honours Project - Risk Assesment
Risk | Likelihood | Loss | Severity | Priority | Contigency 1 | Contigency 2
Database crashes and losses all data | 8 | 10 | 80 | 1 | Have data all backed up on a local database, so it is easy to transfer to the local one | Store all sql statements so I can easily run them again
Other projects take longer than expected | 9 | 8 | 72 | 2 | Have set days where I only focus on honours project, so I don’t let other projects affect it | Spend more time on honours project to catch up on what hours were lost from the other projects
Project scope expands | 9 | 8 | 72 | 2 | Reorganise and reprioritise requirements, so I'm not trying to do too much within the time frame | Discuss scope with supervisor and organise the most important/relevant aspects of project
Loss of file data | 7 | 10 | 70 | 3 | Have everything backed up on github so I can access the files wherever I am | Back up files on external hard drive
Ethics not approved and needs changed | 8 | 8 | 64 | 4 | Make the changes to the ethics first priority and deal with it immediaely | ~
Laptop crashes | 6 | 10 | 60 | 5 | Have all files stored online so I can easily move to another pc | ~
Cant connect to vpn | 7 | 8 | 56 | 6 | Have everything local as well as on vpn | ~
I become ill | 7 | 7 | 49 | 7 | Contact supervisor to let them know that this may affect progress | ~
Loss of wifi | 6 | 7 | 42 | 8 | Have locations to goto where wifi will be available | ~
Participants pull out of project | 5 | 8 | 40 | 9 | Try to get more particpants than needed so you have them as back up | ~
Device stops working | 5 | 8 | 40 | 9 | Be able to show on emulator or an alternate device | ~